|  |
| --- |
| **Project Overview** |
| **Problem Statement**: Evidence based-care has shown an increased one and five-year survival rates for vascular procedure patients that are discharged an antiplatelet and statin medications. Currently at Hospital X for CY 2017 for all vascular procedures (CEA, Endo AAA Repair, Infra-inguinal bypass, Open AAA repair, PVI, Supra-inguinal Bypass and Thoracic and Complex EVAR) discharge ASA is prescribed to 75.1% of our patients and discharged Statins are prescribed 76.3% of the time. To improve the long-term vascular health of our patients we will work on improving prescription of anti-platelets and statins to appropriate patients.  |
| **Goal**: Increase discharge medications ASA and discharge Statins to appropriate vascular patient to 90% by Dec 31, 2018 |
| **Scope**: For this project it will involve patients undergoing CEA, Endo AAA Repair, Infra-Inguinal Bypass, Open AAA Repair, Peripheral Vascular Intervention, Supra-Inguinal Bypass, Thoracic and Complex EVAR at Hospital X for CY 2018 |
| **Deliverable(s)**: Review baseline data by surgical procedure. Form a multi-discipline team to identify barriers to compliance and opportunities for improvement.  |
| **Resources Required**: Multi-discipline team including: Vascular Surgeon, Acute Care ACP, Acute Care RN, Quality, and Data Analysis Team member. Add additional personnel as needed.  |
| **Key Metrics** |  **Milestones** |
| **Outcome Metrics:**Increase DC ASA and Statin to appropriate vascular patients to 90% |  **Milestone / Description:** Complete QI Project Charter Review baseline data by surgical procedureMulti-discipline team formationIdentify barriers / Root cause analysisIdentify potential improvementsTest improvements on small scaleEvaluate progress- and implement changesMonitor and hardwires changes | **Date (mm/yy):**Feb 2018March 2018March 2018March 2018April 2018May 2018June 2018July – Dec 2018 |
| **Process Metrics:**Most current Power Plan addresses ASA and Statin on DC100% of Fellows and ACPs are utilizing the appropriate Power Plan |
| **Team Members** |
| **Exec Sponsor**:  | **Clinical Sponsor**:  |
| **Sponsor**:  | **Process Owner**:  |
| **Project Leader**:  | **Team Members** |